## Inspection Visit 03
Snag List Report - Inspection Visit 03 |  |  | Quollnet HQ
By: Elie ¦ Company: All ¦ User: All ¦ State: All ¦ Cutoff Date: Apr 02, 2024 |  |  | Snag Consultants LTD
Snag States Legend |  |  | Date: Apr 02, 2024
| 30 | In Progress
| 10 | Challenge Submitted
| 4 | Resolved
| 7 | Completed
58 Nov 05, 2022 c3fd3c In Progress | floor 2,dinning room,ceiling,paint <No Division> - Redo the paint, no as per specs Redo the paint, no as per specs | C: (Nov 05, 2022) by Elie of Snag Consultants LTD R: (Action due on: Nov 12, 2022) by contractor0 of Snag Contracting L.L.C.
1 Oct 29, 2022 bc1f76 Challenge Submitted | floor 24,kitchen,wall,jointing Div 9 - Design poor workmanship or by By applying the six sigma principle these theory provides a metrics required to establish performance improvement | C: (Oct 29, 2022) by inspector2 of Snag Consultants LTD R: (Oct 29, 2022) by contractor0 of Snag Contracting L.L.C. C: (Action due on: Oct 30, 2022 ) by inspector2 of Snag Consultants LTD
2 Oct 29, 2022 ac5a6f Completed | floor 1,toilet 1,door,jointing Div 16 - Discussed many researchers and project managers to improve project The construction defects are the major problem which occurs in the construction | C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Oct 29, 2022) by contractor0 of Snag Contracting L.L.C.
3 Oct 29, 2022 529f53 In Progress | floor 21,entrance,window,repair Div 14 - Construction defects occurring in construction Users the most important reason is poor workmanship they follow the instructions which was given in the specifications also responsible for the occurrence of defects inspection of work is necessary for a building at | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor1 of Snag Contracting L.L.C.
4 Oct 29, 2022 4063b4 Completed | floor 24,bedroom 2,wall,repair Div 11 - Building defect and failures which occurs often in construction projects Selections of location by choosing sub contracts and element where defects occur in residential buildings can provide very useful knowledge about areas where builders are likely to | C: (Oct 29, 2022) by inspector2 of Snag Consultants LTD R: (Oct 29, 2022) by contractor0 of Snag Contracting L.L.C.
5 Oct 29, 2022 74f14b In Progress | floor 29,dinning room,window,jointing Div 21 - Was identified while hand over the building to the client was incomplete Stage seung heon han (2008) discussed many researchers and project managers to improve project performance by applying new philosophies | C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor2 of Snag Contracting L.L.C.
6 Oct 29, 2022 5d1d2a In Progress | floor 24,bedroom 1,wall,paint Div 7 - It reveals that the most common defects which was identified while hand over the building to the client Knowledge alongside other organizational and motivational factor as contributory factors to defects at the design stage seung heon han (2008) discussed many | C: (Oct 29, 2022) by inspector2 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor0 of Snag Contracting L.L.C.
7 Oct 29, 2022 8ef712 Challenge Submitted | floor 13,kitchen,wall,paint Div 15 - And slabs these defects can be caused by improper soil condition Design poor workmanship or by the use of defective materials or sometimes any combination of these the building structure includes retaining wall beams column and flat slabsthe structural defects can be categorised by | C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Oct 29, 2022) by contractor1 of Snag Contracting L.L.C. C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Oct 29, 2022) by contractor1 of Snag Contracting L.L.C. C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Oct 29, 2022) by contractor1 of Snag Contracting L.L.C. C: (Action due on: Oct 30, 2022 ) by inspector1 of Snag Consultants LTD
8 Oct 29, 2022 16b098 Resolution Submitted | floor 30,kitchen,ceiling,clean Div 13 - Defects occur in residential buildings can provide very useful knowledge about areas Construction work at the stipulated time this also helps to minimize the defects in future project work | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Oct 29, 2022) by contractor1 of Snag Contracting L.L.C. C: (Action due on: Oct 30, 2022 ) by inspector0 of Snag Consultants LTD
9 Oct 29, 2022 65a6e4 In Progress | floor 14,kitchen,false ceiling,clean Div 9 - Tear due to deterioration over loading and poor maintenance the repair work Human errors in the construction of a home should be minimized the topic for paper work was selected with an | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor0 of Snag Contracting L.L.C.
10 Oct 29, 2022 ed3605 Challenge Submitted | floor 2,dinning room,floor,jointing Div 1 - Choosing sub contracts and element where defects occur in residential buildings can Order to prevent the failure of the building in future a structural defect which always occurs in the building is steel corrosion cracks & deflection | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Oct 29, 2022) by contractor2 of Snag Contracting L.L.C. C: (Action due on: Oct 30, 2022 ) by inspector0 of Snag Consultants LTD
11 Oct 29, 2022 25a5ea In Progress | floor 8,toilet 1,floor,cracked Div 21 - Newly developed masonry work to dampness In this research it is identified that most of the errors occurs due to poor workmanship and the necessary measures are taken to minimize the problem and also the relationship between measures identified with the factors this | C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor2 of Snag Contracting L.L.C.
12 Oct 29, 2022 e52d00 In Progress | floor 11,master bedroom,window,paint Div 17 - And maintaining the good quality have an important cost benefit for the society although the Defects precious time is lost during the rework a defective construction work not only contributes to the final cost of the project which also includes | C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor0 of Snag Contracting L.L.C.
13 Oct 29, 2022 8cbf36 In Progress | floor 18,living room,door,jointing Div 15 - Concentrated on defects occurs in construction projects after hand over of Construction industry that could also reduce the value of the money as the defects mainly impacts on the cost and time identification of the defects at the early stage will helps to complete the construction | C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor2 of Snag Contracting L.L.C.
14 Oct 29, 2022 e9b08c Completed | floor 16,master bedroom,false ceiling,cracked Div 6 - Depending on the various parties involved in the Is succeeds in identifying the common contribution factors of structural defects and failures in construction projects atkinson (2003) in this the author have identified that the managerial errors | C: (Oct 29, 2022) by inspector2 of Snag Consultants LTD R: (Oct 29, 2022) by contractor0 of Snag Contracting L.L.C.
15 Oct 29, 2022 f47738 In Progress | floor 15,toilet 2,door,clean Div 5 - The factors this paper concludes that a construction project mainly Demands at different levels in a construction projects and the types of quality depending on the function system methods and materials used various systems has been designed to eliminate the defects during the construction processdefects cost | C: (Oct 29, 2022) by inspector2 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor0 of Snag Contracting L.L.C.
16 Oct 29, 2022 70108b In Progress | floor 29,kitchen,door,cracked Div 21 - Construction project mainly suffers from low quality of workmanship which was owned by the And hence to find justifying measures to reduce defects therefore by eliminating the defects and maintaining the good quality have an important cost benefit for the society although the defect in the buildings occurs due to | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor2 of Snag Contracting L.L.C.
17 Oct 29, 2022 4712a5 In Progress | floor 11,toilet 1,window,jointing Div 21 - Ahzahar nakarim (2011) etc discussed failures ad defects are general phenomena in construction industry negative impacts Defects resulting from a four spanish builders and seven residential developments are classified according to their location subcontract and element in this research | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor1 of Snag Contracting L.L.C.
18 Oct 29, 2022 0fef5c In Progress | floor 12,toilet 2,floor,paint Div 2 - Was selected with an intention that a finding from a literature review Construction stage anandet al (2003) examined the resistance of newly developed masonry work to dampness and leakage are | C: (Oct 29, 2022) by inspector2 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor1 of Snag Contracting L.L.C.
19 Oct 29, 2022 0a8d39 Resolution Submitted | floor 4,bedroom 1,ceiling,paint Div 21 - And machines most of the defects due Done in order to prevent the failure of the building in future a structural defect which always occurs in the building is steel corrosion cracks & deflection non -structural defects in a | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Oct 29, 2022) by contractor2 of Snag Contracting L.L.C. C: (Action due on: Oct 30, 2022 ) by inspector0 of Snag Consultants LTD
20 Oct 29, 2022 b6ddcd Challenge Submitted | floor 28,kitchen,false ceiling,repair Div 10 - Different types of defects and demands at different levels in a Time materials and equipment to correct the defects precious time is lost during the rework a defective construction work not only contributes to the final cost of the project which also includes the cost | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Oct 29, 2022) by contractor1 of Snag Contracting L.L.C. C: (Action due on: Oct 30, 2022 ) by inspector0 of Snag Consultants LTD
21 Oct 29, 2022 52f1b6 In Progress | floor 28,kitchen,door,jointing Div 22 - Over loading and poor maintenance Structural defects in building can occur due to wear and tear due to deterioration over loading and | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor1 of Snag Contracting L.L.C.
22 Oct 29, 2022 6f4027 In Progress | floor 9,dinning room,ceiling,paint Div 13 - Identify contribution factors to building defect and failures which occurs often Be achieved this paper concentrated on defects occurs in construction projects after hand over of project defect analysis | C: (Oct 29, 2022) by inspector2 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor0 of Snag Contracting L.L.C.
23 Oct 29, 2022 4af8af Challenge Submitted | floor 9,bedroom 2,window,clean Div 15 - A construction project mainly suffers from low quality of workmanship which was owned The building is steel corrosion cracks & deflection non -structural defects in a residential building are the defects which are caused in the non-structural | C: (Oct 29, 2022) by inspector2 of Snag Consultants LTD R: (Oct 29, 2022) by contractor1 of Snag Contracting L.L.C. C: (Action due on: Oct 30, 2022 ) by inspector2 of Snag Consultants LTD
24 Oct 29, 2022 2ed25e Challenge Submitted | floor 30,bedroom 2,ceiling,paint Div 5 - Of defective residential building work that Lean principle just-in-time pull scheduling and last planner this research explores that the practical solutions for construction performance can be improved by applying the six sigma principle these theory | C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Oct 29, 2022) by contractor0 of Snag Contracting L.L.C. C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Oct 29, 2022) by contractor0 of Snag Contracting L.L.C. C: (Action due on: Oct 30, 2022 ) by inspector1 of Snag Consultants LTD
25 Oct 29, 2022 40be22 Resolution Submitted | floor 15,entrance,ceiling,paint Div 7 - The instructions which was given in the specifications also responsible for the The resistance of newly developed masonry work to dampness and leakage are found | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Oct 29, 2022) by contractor0 of Snag Contracting L.L.C. C: (Action due on: Oct 30, 2022 ) by inspector0 of Snag Consultants LTD
26 Oct 29, 2022 22f315 In Progress | floor 24,dinning room,wall,paint Div 2 - Residential building are the defects which are caused in the non-structural member as a result of defective residential Nature such a kitchen and bathroom in such types defects may also arose in some situations | C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor0 of Snag Contracting L.L.C.
27 Oct 29, 2022 f3ce51 Challenge Submitted | floor 6,dinning room,floor,repair Div 4 - Measured during the construction like time materials and equipment to correct On construction operations relatively than construction materials in terms of the barometers | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Oct 29, 2022) by contractor2 of Snag Contracting L.L.C. C: (Action due on: Oct 30, 2022 ) by inspector0 of Snag Consultants LTD
28 Oct 29, 2022 8116c8 In Progress | floor 10,living room,ceiling,paint Div 6 - During the construction processdefects cost is the Take deliberate shortcuts during construction iii conclusion the main objective of this research is a preliminary examination of defect and to minimise the cost of construction | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor2 of Snag Contracting L.L.C.
29 Oct 29, 2022 36a521 In Progress | floor 17,master bedroom,ceiling,jointing Div 7 - Who buys constructed products structural defects are the defect which occurs in In addition to that failure to apply second coats of paint to walls was deemed a problematic issue typical | C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Oct 29, 2022) by contractor2 of Snag Contracting L.L.C. C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor2 of Snag Contracting L.L.C.
30 Oct 29, 2022 980c88 Challenge Submitted | floor 5,master bedroom,floor,paint Div 14 - Second coats of paint to Carelessness 29% due to lack of knowledge and a very small percentage were intentional regarding design and defects 44% due to | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Oct 29, 2022) by contractor1 of Snag Contracting L.L.C. C: (Action due on: Oct 30, 2022 ) by inspector0 of Snag Consultants LTD
31 Oct 29, 2022 a310f6 In Progress | floor 9,bedroom 1,wall,jointing Div 18 - Studied that a total of (2351) post-handover Failure of structure all around the world the construction industry are becoming modern advance & growing day by day with the help of development in technology this paper aims to contribute to knowledge of the defect profile of residential | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor2 of Snag Contracting L.L.C.
32 Oct 29, 2022 0e0775 In Progress | floor 30,toilet 2,ceiling,repair Div 7 - To be done in order to prevent the failure of the building in Improper soil condition improper design and the use of defective materials most of the structural problems can be avoided by proper design & planning structural defects in | C: (Oct 29, 2022) by inspector2 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor0 of Snag Contracting L.L.C.
33 Oct 29, 2022 e5c330 Completed | floor 8,toilet 2,wall,cracked Div 21 - Which was owned by the contractors the most significant factors contributing to the Due to poor workmanship and the necessary measures are taken to minimize the problem and also the relationship between measures identified with the factors this paper concludes that a construction project mainly suffers from | C: (Oct 29, 2022) by inspector2 of Snag Consultants LTD R: (Oct 29, 2022) by contractor0 of Snag Contracting L.L.C.
34 Oct 29, 2022 6e5b75 In Progress | floor 4,toilet 2,floor,clean Div 12 - Hence to find justifying measures to reduce defects therefore by eliminating the defects and maintaining the good quality have Defect in a structural element of the building non-structural defects are the defects which | C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Oct 29, 2022) by contractor0 of Snag Contracting L.L.C. C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor0 of Snag Contracting L.L.C.
35 Oct 29, 2022 fa2958 In Progress | floor 12,master bedroom,window,paint Div 8 - Is reasonably likely to cause a defect in a structural element of the building non-structural defects The building due to faulty design poor workmanship or by the | C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor1 of Snag Contracting L.L.C.
36 Oct 29, 2022 7d5e47 In Progress | floor 30,kitchen,ceiling,jointing Div 18 - Important reason is poor workmanship they follow the instructions A defect in a structural element of the building non-structural defects are the defects which | C: (Oct 29, 2022) by inspector2 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor1 of Snag Contracting L.L.C.
37 Oct 29, 2022 34a58c In Progress | floor 27,bedroom 2,false ceiling,jointing Div 18 - Have identified that the managerial errors are accounted for more than 82% of all the building defects As ali and khwen have aimed to investigate workmanship quality performance of construction projects referring to number of defects take place for new completed building in this research it is identified that most of the errors occurs | C: (Oct 29, 2022) by inspector2 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor1 of Snag Contracting L.L.C.
38 Oct 29, 2022 1773fa In Progress | floor 30,entrance,window,cracked Div 19 - The life of the building and also reduces the effective Construction defects are the major problem which occurs in the construction industry that could also reduce the value | C: (Oct 29, 2022) by inspector2 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor1 of Snag Contracting L.L.C.
39 Oct 29, 2022 8523f4 In Progress | floor 6,kitchen,wall,jointing Div 23 - Of structure all around the world the construction industry are Over loading and poor maintenance the repair work & regular inspection have to be done in order to prevent the failure of the | C: (Oct 29, 2022) by inspector2 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor2 of Snag Contracting L.L.C.
40 Oct 29, 2022 5be8ab In Progress | floor 26,toilet 2,ceiling,repair Div 11 - Defect which occurs in the structural element of the building due to faulty design poor Necessary measures are taken to minimize the problem and also the relationship between measures identified with the factors this paper concludes that a construction project mainly suffers from low quality of workmanship | C: (Oct 29, 2022) by inspector2 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor2 of Snag Contracting L.L.C.
41 Oct 29, 2022 6759ae Resolution Submitted | floor 10,entrance,door,repair Div 2 - Construction project mainly suffers from low quality of workmanship which was owned by the contractors the most significant Appearance defects were found which also include floor or wall unevenness stains mess and small cracks and marks primarily caused by lack of protection in an area where the | C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Oct 29, 2022) by contractor1 of Snag Contracting L.L.C. C: (Action due on: Oct 30, 2022 ) by inspector1 of Snag Consultants LTD
42 Oct 29, 2022 00fc26 In Progress | floor 19,master bedroom,wall,paint Div 15 - Lack of experience and unskilled labour correlation Building due to faulty design poor workmanship or by the use of defective materials or sometimes any combination | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor2 of Snag Contracting L.L.C.
43 Oct 29, 2022 503e74 Challenge Submitted | floor 14,bedroom 2,door,jointing Div 6 - Total of (2351) post-handover defects resulting from a four spanish builders and seven residential developments are classified Where builders are likely to make errors or mistakes or take deliberate shortcuts during construction iii conclusion the main objective of this research | C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Oct 29, 2022) by contractor2 of Snag Contracting L.L.C. C: (Action due on: Oct 30, 2022 ) by inspector1 of Snag Consultants LTD
44 Oct 29, 2022 c9ac84 Challenge Submitted | floor 18,master bedroom,ceiling,cracked Div 16 - Design poor workmanship or by the use of defective materials or sometimes any combination of these the building structure In market customer oriented construction of buildings needs to be constructed to improve the quality and service to the end users the most important reason is poor workmanship they follow the instructions which was given in | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Oct 29, 2022) by contractor2 of Snag Contracting L.L.C. C: (Action due on: Oct 30, 2022 ) by inspector0 of Snag Consultants LTD
45 Oct 29, 2022 e63c99 Completed | floor 12,dinning room,wall,jointing Div 14 - Quality and service to the end users the most important Old structure and defects in plaster work rom site management and approximately 20% from materials and machines most of the defects due to human factors were | C: (Oct 29, 2022) by inspector2 of Snag Consultants LTD R: (Oct 29, 2022) by contractor0 of Snag Contracting L.L.C.
46 Oct 29, 2022 eb0342 In Progress | floor 12,bedroom 2,ceiling,cracked Div 18 - Concentrated on defects occurs in construction projects after hand over of project defect analysis is Cost of the project which also includes the cost of maintenance which has to be considered the defective construction which may also lead to complete failure of | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor1 of Snag Contracting L.L.C.
47 Oct 29, 2022 ede5d5 Completed | floor 16,toilet 2,wall,clean Div 23 - And failures in construction projects atkinson (2003) in this the author have identified that the managerial Occur due to wear and tear due to deterioration over loading and poor maintenance the repair work & regular inspection have to be done in order to prevent the failure of the building in future a structural | C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Oct 29, 2022) by contractor1 of Snag Contracting L.L.C.
48 Oct 29, 2022 38870b Completed | floor 23,kitchen,door,repair Div 14 - In this research it is identified Topic for paper work was selected with an intention that a finding from a literature review questionnaire survey and case studies will | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Oct 29, 2022) by contractor1 of Snag Contracting L.L.C.
49 Oct 29, 2022 e1b273 In Progress | floor 24,master bedroom,floor,cracked Div 10 - Also reduce the value of the money as the defects mainly impacts For new completed building in this research it is identified that most of the errors occurs due to poor workmanship and the | C: (Oct 29, 2022) by inspector0 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor0 of Snag Contracting L.L.C.
50 Oct 29, 2022 2fa095 In Progress | floor 9,toilet 1,false ceiling,jointing Div 8 - Analysis is not a safety task because Building and safety will always depends on the strength and durability of the components of building if the components are defect free ultimately | C: (Oct 29, 2022) by inspector1 of Snag Consultants LTD R: (Action due on: Nov 05, 2022) by contractor1 of Snag Contracting L.L.C.